## Master Schedule
🗓 Syncademic v2.0 — Master Sprint Schedule
Project: Exam Schedule Generator · Team: Alon · Ron · Guy · Niv · Lotem · Updated: May 2026
Jira | Story | Task Description | Assignee | Status | Sprint | Epic
◀ SPRINT 1 — v1.0 Core CLI System ▶
SCRUM-5 | Epic 1 | Core Domain & Architecture | — |  | 1 | E1
SCRUM-10 | 1.1 | Define Core Domain Models | Guy | ✅ Done | 1 | E1
SCRUM-11 | 1.2 | Define System Interfaces (ABCs) | Guy | ✅ Done | 1 | E1
SCRUM-6 | Epic 2 | Data Ingestion — Input Adapters | — |  | 1 | E2
SCRUM-12 | 2.1 | Implement File-Based Data Readers | Guy | ✅ Done | 1 | E2
SCRUM-13 | 2.2 | Input Validation & Error Handling | Guy | ✅ Done | 1 | E2
SCRUM-7 | Epic 3 | Scheduling Engine — Core Logic | — |  | 1 | E3
SCRUM-14 | 3.1 | Implement Exact Conflict Strategy | Ron | ✅ Done | 1 | E3
SCRUM-15 | 3.2 | Backtracking Generator (MCV) | Ron | ✅ Done | 1 | E3
SCRUM-16 | 3.3 | AppController — CLI Orchestration | Alon | ✅ Done | 1 | E3
SCRUM-8 | Epic 4 | Output Generation — Adapters | — |  | 1 | E4
SCRUM-17 | 4.1 | Text File Exporter | Alon | ✅ Done | 1 | E4
SCRUM-9 | Epic 5 | E2E Testing & Agile Documentation | — |  | 1 | E5
SCRUM-18 | 5.1 | Unit Tests — Domain Layer | Guy | ✅ Done | 1 | E5
SCRUM-19 | 5.2 | Unit Tests — Engine Layer | Guy | ✅ Done | 1 | E5
SCRUM-20 | 5.3 | Integration & E2E Tests | Guy | ✅ Done | 1 | E5
SCRUM-21 | 5.4 | Agile Docs v1.0 (SRS, SDD) | Lotem | ✅ Done | 1 | E5
◀ SPRINT 2 — v2.0 REST API + Frontend ▶
SCRUM-22 | Epic 6 | REST API Layer (FastAPI) | — |  | 2 | E6
SCRUM-23 | 6.1 | FastAPI App Factory + CORS + Lifespan | Alon | ✅ Done | 2 | E6
SCRUM-24 | 6.2 | Session Management (SessionStore) | Alon | ✅ Done | 2 | E6
SCRUM-75 | 6.3 | POST /api/schedules/generate (async) | Ron | ✅ Done | 2 | E6
SCRUM-76 | 6.4 | GET /api/generate/status | Ron | ✅ Done | 2 | E6
SCRUM-123 | 6.5 | Paginated Exporter (thread-safe) | Ron | ✅ Done | 2 | E6
SCRUM-124 | 6.6 | JSON Cache Adapter (disk persist) | Alon | ✅ Done | 2 | E6
SCRUM-131 | 6.7 | Pydantic Schemas & Exception Handlers | Alon | ✅ Done | 2 | E6
SCRUM-25 | 6.8 | InMemoryDataProvider Adapter | Alon | ✅ Done | 2 | E6
SCRUM-67 | 6.9 | POST /api/data/courses/upload | Ron | 🔄 In Progress | 2 | E6
SCRUM-68 | 6.10 | POST /api/data/periods/upload | Ron | 🔄 In Progress | 2 | E6
SCRUM-26 | 6.11 | GET /api/schedules (pagination) | Ron | ☐ To Do | 2 | E6
SCRUM-27 | Epic 7 | Frontend — Presentation Layer | — |  | 2 | E7
SCRUM-80 | 7.1 | Frontend App Shell (React + Vite) | Niv | ☐ To Do | 2 | E7
SCRUM-81 | 7.2 | InputScreen — File Upload UI | Niv | ☐ To Do | 2 | E7
SCRUM-82 | 7.3 | OutputScreen — Schedule Calendar View | Niv | ☐ To Do | 2 | E7
SCRUM-83 | 7.4 | Schedule Pagination Controls | Niv | ☐ To Do | 2 | E7
SCRUM-84 | 7.5 | API Integration (Axios hooks) | Niv | ☐ To Do | 2 | E7
SCRUM-133 | 7.6 | Design Tokens (PROGRAMME_COLOURS) | Lotem | ☐ To Do | 2 | E7
SCRUM-134 | 7.7 | Shared Component Library | Niv | ☐ To Do | 2 | E7
SCRUM-28 | Epic 8 | QA — GUI, API & Performance | — |  | 2 | E8
SCRUM-29 | 8.1 | Performance & Stress Testing (v2) | Guy | ✅ Done | 2 | E8
SCRUM-30 | 8.2 | GUI Component Tests (Playwright) | Guy | ☐ To Do | 2 | E8
SCRUM-31 | 8.3 | API Integration Tests | Guy | ☐ To Do | 2 | E8
SCRUM-32 | 8.4 | QA Coverage Report (≥80%) | Guy | ☐ To Do | 2 | E8
SCRUM-33 | 8.5 | User Manual / Local Config Docs | Lotem | ☐ To Do | 2 | E8
LEGEND
✅ Done | Task completed and merged
🔄 In Progress | Currently being worked on
☐ To Do | Not yet started